Policy Verification System

Hallucination and Citation Verifier for Policy Question Answering

Final Implementation Plan

Solo project  ·  8–12 weeks  ·  Local-first

August 2026

# 1.  Context

Build a local AI system that answers questions about university policies, shows the evidence, breaks each answer into separate claims, checks every claim against the retrieved text, and refuses to answer when the evidence isn't good enough.

Goal: correctness, transparency, explainability, usability. Runs locally — no deployment.

In plain words: normal AI chatbots make things up and you can't tell. This one shows you every fact it stated, points at the exact policy text behind it, and stays quiet when it doesn't actually know.

## Locked decisions

| Area | Decision |
| --- | --- |
| Corpus | 3–4 universities × 5–6 policy types ≈ 20–25 documents, downloaded by hand |
| Corpus in git | Commit a manifest (URLs, dates, checksums) + code — not the PDFs |
| Project shape | Core Python package + Streamlit that imports it — no logic in the UI file |
| LLM | Qwen3 4B via Ollama first, 8B later (config change) |
| Embedding | BAAI/bge-base-en-v1.5 on CPU — keeps all VRAM free for Qwen |
| Vector store | Chroma — persistence and metadata filtering built in |
| Retrieval | Dense search + filter by university |
| Verification | NLI model + numeric guard + citation-exists check |
| Correction | Drop unsupported claims, show what was removed |
| Storage | JSONL log files — no database |

Environment: use a Python 3.11 or 3.12 virtual environment. The installed Python 3.14 will fight PyTorch and cost you days.

# 2.  Repository Structure

policy-verification-system/

├── README.md

├── requirements.txt

├── config.yaml                  # every setting in one place

├── data/

│   ├── manifest.yaml            # COMMITTED: sources, dates, checksums

│   ├── raw/                     # gitignored: downloaded files

│   ├── processed/               # gitignored: cleaned documents

│   └── index/                   # gitignored: chroma database

├── src/policyverify/

│   ├── config.py

│   ├── schema.py                # * data shapes — write this FIRST

│   ├── ingest/

│   │   ├── fetch.py             # download files listed in manifest

│   │   ├── extract.py           # PDF/HTML -> plain text

│   │   └── normalize.py         # -> Document with sections

│   ├── indexing/

│   │   ├── chunk.py             # split documents into searchable pieces

│   │   └── store.py             # Chroma wrapper

│   ├── retrieve.py              # find relevant chunks

│   ├── llm.py                   # * the one place the model is called

│   ├── generate.py              # ask model for JSON claims

│   ├── verify/

│   │   ├── nli.py               # does the passage support the claim?

│   │   ├── numeric.py           # do the numbers match?

│   │   └── citation.py          # does the cited section exist?

│   ├── abstain.py               # decide whether to refuse

│   └── pipeline.py              # ties everything together

├── app/streamlit_app.py         # thin UI, no logic

├── scripts/

│   ├── build_index.py

│   ├── ask.py                   # ask one question from the terminal

│   └── evaluate.py              # run the test set -> metrics table

├── eval/

│   ├── adversarial.jsonl        # your trick questions

│   └── results/

└── tests/

├── conftest.py              # FakeLLM fixture

└── test_*.py

Why split the core from Streamlit: Streamlit re-runs the whole file on every click, so anything living there can't be tested. Keeping logic in src/ means your tests, your CLI, and your UI all run the exact same code.

# 3.  The Two Contracts — Decide These First

Everything depends on them, so write them before any other code.

### 1.  Citation ID

Format: {university}/{policy}/{section}  →  uni_a/academic_integrity/4.2

Three functions: parse, validate, resolve-to-chunk. Use the document's own numbering where it exists, heading names where it doesn't.

### 2.  Data shapes (schema.py, using Pydantic)

| Model | Fields |
| --- | --- |
| Document | university, policy_type, title, source_url, sections[] |
| Chunk | id, text, citation_id, university, policy_type, section_path |
| Claim | text, citation_ids[] |
| ClaimVerdict | claim, status (SUPPORTED / REFUTED / NEUTRAL), score, evidence_chunk_ids[], checks{} |
| Answer | question, claims_kept[], claims_removed[], abstained, reason, timings{} |

Why Pydantic: it checks the model's output actually has the right shape. When the LLM returns something malformed, you get a clear error instead of a confusing crash three functions later.

# 4.  Implementation Phases

## Phase 0 — Setup & Spikes  (Week 1)

A "spike" is a quick throwaway test to check something works before you build on top of it.

| Spike | What you're checking | Fallback |
| --- | --- | --- |
| Corpus | Download one policy from 5 universities, extract text, look at it. Keep the 3–4 that come out clean. | Prefer universities publishing HTML; drop PDF-only ones |
| VRAM | Run Qwen3 4B in Ollama with the embedder + NLI on CPU. Watch nvidia-smi. | Smaller model; confirm the small models really are on CPU |
| NLI | 20 hand-written claim/passage pairs through 2–3 checkpoints (DeBERTa-v3 MNLI/FEVER/ANLI, Vectara HHEM) | If all are weak on policy text, plan to add the LLM-judge tier |

Also: virtual environment, requirements.txt, repo skeleton, git, schema.py written, manifest.yaml.

Pick your universities based on which ones extract cleanly. Nothing requires a specific institution — choosing the easy ones is smart, not cheating.

✓  Done when: import policyverify works · schema exists · manifest lists your chosen universities.

## Phase 1 — Ingestion  (Week 2)

fetch.py downloads files from the manifest and verifies checksums → extract.py turns PDF (PyMuPDF) and HTML (BeautifulSoup) into text → normalize.py produces a Document with a section tree.

Every university formats policies differently. Converting them all into one shape here means nothing downstream has to care where a document came from.

✓  Done when: all ~25 documents become valid Document objects, and you have read 3 of them by hand to confirm the text is clean.

## Phase 2 — Chunking & Index  (Week 3)

chunk.py splits on headings — never mid-section — and attaches university, policy type, section path, and citation ID to every chunk. store.py wraps Chroma. scripts/build_index.py builds it.

Write an index manifest recording which embedding model built the index.

This matters more than it looks: if you rebuild with a different embedding model and forget, search silently returns nonsense with no error message. It's the most common bug in RAG systems.

✓  Done when: the index builds in one command and a manual search returns obviously relevant chunks.

## Phase 3 — Retrieval & Generation  (Week 4)

retrieve.py — dense search plus an optional university filter. llm.py — one generate(prompt) -> str function with Ollama behind it. generate.py — ask the model for JSON claims with citation IDs, validate with Pydantic, retry once, then fail loudly.

Use Ollama's JSON format mode. Never write prose and then try to parse claims back out of it — that approach breaks constantly.

✓  Done when: scripts/ask.py "question" returns claims with citations. The answers will be mediocre. That's expected — the verifier is what fixes it, so don't spend this week tuning prompts.

## Phase 4 — The Verifier  (Weeks 5–6)  ·  the core

This is the heart of the project. Spend your time here.

- nli.py — for each claim × each cited passage, decide supported / refuted / neutral with a score

- numeric.py — pull numbers, percentages, and dates out of both claim and passage, flag mismatches

- citation.py — two separate checks: does the cited section exist (made-up citation), and does that passage support the claim (wrong citation)

- pipeline.py — wire retrieve → generate → verify into an Answer

An NLI model just answers "does text A prove text B?" That's exactly the question you need, it runs on CPU, and it's more reliable than asking the LLM to grade itself — a model checking its own work tends to repeat its own mistakes.

The numeric guard is small but catches the errors that matter most here: "75%" vs "80%" is the kind of mistake that actually hurts someone.

✓  Done when: every claim has a verdict, a score, and evidence IDs.

## Phase 5 — Abstention & Correction  (Week 7)

abstain.py — one threshold over claim scores, read from config.yaml. Unsupported claims move into claims_removed instead of being silently deleted. Abstain entirely when too little survives.

Keeping removed claims is the whole transparency feature — the user sees what the system tried to say and chose not to.

✓  Done when: the system refuses to answer a question your corpus doesn't cover, and explains why.

## Phase 6 — Adversarial Dataset  (Week 8)

60–80 trick questions across five categories: cross-university confusion (your signature trap) · numeric traps · unanswerable-but-plausible · negation/exception · false premise.

Split into a tuning set and a held-out set. Tune the abstention threshold on the tuning set only.

Tuning and reporting on the same questions makes your results meaningless — you'd only be proving it works on the questions you tuned it for.

## Phase 7 — Streamlit UI  (Week 9)

Question box · university filter · color-coded claims · expandable evidence per claim · abstention banner · removed-claims panel. It imports pipeline.py and renders. No logic.

✓  Done when: UI and CLI give identical verdicts for the same question — proof they share one core.

## Phase 8 — Evaluation  (Week 10)

scripts/evaluate.py runs the held-out set and produces five metrics. Log every run to JSONL.

| Metric | Meaning |
| --- | --- |
| Claim verification P/R | Are "supported" claims really supported? Did you catch all the good ones? |
| Citation accuracy | Section exists and actually supports the claim |
| Hallucination rate | % of claims not backed by the evidence cited |
| Abstention quality | 2×2 — answered vs. abstained, against answerable vs. unanswerable |
| Latency | Time split across retrieve / generate / verify |

Track false abstention explicitly. A system that refuses everything gets a perfect hallucination score and is completely useless.

✓  Done when: one command produces the metrics table.

## Phase 9 — Hardening & Deliverables  (Weeks 11–12)

Hybrid retrieval (BM25 + RRF, ~10 lines, real gain on exact numbers) · error analysis (~15 failures, categorized) · README + architecture diagram · 5-minute demo script (clean answer → trap caught → abstention) · buffer.

The README and demo script matter more than they feel like they should — people judge the project through them, not by reading your code.

# 5.  Risks

| Risk | Mitigation |
| --- | --- |
| PDF extraction is garbage | Choose universities by extraction quality in Phase 0; prefer HTML |
| LLM returns invalid JSON | JSON mode + Pydantic + one retry + fail loudly. Never silently accept bad output. |
| NLI model weak on policy text | Test in Phase 0, not week 6. Fallback: add the LLM-judge tier. |
| VRAM runs out | Qwen3 4B first; confirm embedder and NLI are on CPU |
| Chunks wrong size | Make it a config value; look at real chunks early |
| Scope creep | Reranker, re-retrieval loop, multi-hop, conversational memory, Neo4j are a "no" list until the MVP works end-to-end |

# 6.  Testing

pytest plus a ~15-line FakeLLM fixture returning canned responses, so tests run with no GPU and no model.

Test the pure functions — chunk boundaries, citation ID parsing, numeric extraction, threshold logic, schema validation. Don't unit-test answer quality; that's what the evaluation harness is for.

# 7.  Definition of Done

- pytest passes without a GPU

- One command each: rebuild corpus, build index, run evaluation

- Streamlit and CLI give identical verdicts

- The system abstains on a question the corpus doesn't cover

- The system attributes a policy to the right university when two differ

# 8.  If You Fall Behind

Cut in this order: hybrid retrieval → adversarial set down to 40 items and 3 categories (keep cross-university, numeric, unanswerable) → university filter in the UI.

Never cut: the verifier, abstention, the claim-level evidence view, or the evaluation harness. Those four are the project.